## Sheet1
Week | Job done | Milestones | Associated timelines
1 | Game plan & familiarize with new work station | Setup git & project with remote and home base stations | Week 01-02
2 | Set up git, create project with basic scene, familirize with Unity Steam VR implementation, implement grabbing | Implement and test Infinadeck with Unity (need 2 person) | Week 03
3 |  | Implement various trigger mechanisms and needed features | Week 03-06
4 |  | Create test level with all the trigger mechanisms, test it and solve potential flows | Week 06
5 |  | Create tutorial level to explain the input and familiarize the player with walking with the infinadeck, test it and solve potential flows | Week 07
6 |  | Create all the levels with their respective puzzles (game design will come later), add the voice off v.1 in the levels and the clue button | Week 08-10
7 |  | Test the levels, get feedback, solve potential flows and change things if needed | Week 11
8 |  | Make game design (import/create assets), record the voice off in a recording studio and implement it in the game | Week 12-14
9 |  | Test the final product, get feedback, solve potential flows and change things if needed | Week 15
10
11
12
13
14
15