## Sheet1
Week | Job done | Milestones | Associated timelines
1 | Game plan & familiarize with new work station | Setup git & project with remote and home base stations | Week 01-02
2 | Set up git, create project with basic scene, familirize with Unity Steam VR implementation, implement grabbing and throwing | Implement and test Infinadeck with Unity (need 2 person) & change inputs to walk with controllers | Week 03
3 | Test Infinadeck, in game walking with infinadeck, added buttons, clue button with evolving clues, respawning objects, move using controllers, doors V1 | Implement various trigger mechanisms and needed features, writing with voice off, first design | Week 03-06
4 | Finish door, create locks with specific key to unlock, padlock with code to trigger event, cabinet with drawer as a basket, create basic scene with everything | Create test level with all the trigger mechanisms, test it and solve potential flows | Week 06
5 | Correct drawers & doors, create own key, start tutorial and story writing, improve lock and keys, key animation | Create tutorial level to explain the input and familiarize the player with walking with the infinadeck, test it and solve potential flows and presentation | Week 07
6 | Add textures to tutorial and polish it. New puzzle for first level and midterm presentation | Create all the levels with their respective puzzles (game design will come later), add the voice off v.1 in the levels and the clue button | Week 08-11
7 | Midterm presentation and assets for labyrinth and sounds | Test the levels, get feedback, solve potential flows and change things if needed | Week 12
8 | Objects can't fall to the ground, level 1 design first draft, creation of level 1 puzzles | Make game design (import/create assets), record the voice off in a recording studio and implement it in the game | Week 13-14
9 |  | Test the final product, get feedback, solve potential flows and change things if needed report and presentation | Week 15
10 |  | https://assetstore.unity.com/packages/audio/sound-fx/universal-sound-fx-17256#description
11 |  | https://assetstore.unity.com/packages/audio/sound-fx/complete-survival-game-sound-kit-159941
12
13 |  | https://assetstore.unity.com/packages/2d/textures-materials/nature/hedge-labyrinth-package-81576
14
15